## Product Backlog (hidden)
[11 empty] | Level | Priority |  |  |  | Estimate
[11 empty] | 1 | High |  |  |  | Estimated time to complete the work (hour)
[11 empty] | 2 | Medium
[11 empty] | 3 | Low
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB21 | Connect electrical devices and sensors to the ESP8266 | x | x | x | - When connecting the wires correctly, the sensor light will light up. |  | 1 |  |  |  | 1
PB22 | Connect wifi | x | x | x | - Display text "WiFi connection successful" in Serial Monitor. |  | 1 |  |  |  | 1
PB23 | Send devices status to firebase | x | x | x | - Send devices status to firebase |  | 1 |  |  |  | 1
PB24 | Update devices status when firebase database changes | x | x | x | - Update devices status when firebase database changes |  | 1 |  |  |  | 1
PB25 | Send data of sensors to firebase | x | x | x | - Send data of sensors to firebase |  | 1 |  |  |  | 1
PB26 | Alarm when there is an abnormal change from the sensors | x | x | x | - Alarm when there is an abnormal change from the sensors |  | 1 |  |  |  | 1
PB01 | Sign up | Admin, Host, Family member | Create my account so I can use the application | This product backlog allows the actor sign up into the application | - Admin, Host, Family member fills in information such as email, password, fullname, phone number, house key. - Click button [Sign up]. |  | 1 |  |  |  | 2
PB02 | Sign in | Admin, Host, Family member | I want to access to the application by my account so that I can use the application | This product backlog allows the actor sign in into the application | -Admin, User fill email and password. - Click button [Login] |  | 1 |  |  |  | 2
PB06 | View all floors | Host, Family member | I want to see all the floors in my current house. | Allows the actor to see all floors of their house. | - The main screen displays all floors of the house. |  | 2 |  |  |  | 2
PB07 | View all rooms | Host, Family member | I want to see all rooms on the current floor. | Allows the actor to see all rooms of the current floor they click. | - Click on the floor you want to view. - List of all rooms of the floor they clicked on. |  | 2 |  |  |  | 2
PB08 | View all devices | Host, Family member | I want to see all devices on the current room. | Allows the actor to see all devices of the current room they clicked. | - Click on the room you want to view. - List of all devices of the room they clicked on. |  | 1 |  |  |  | 2
PB09 | Set status for device | Host, Family member | I want to turn on and off the device. | Allows the actor to turn on/off devices. | - Click on the device you want to control. - Click on/off for lights or drag the slider from 0 to 3 for fans. |  | 1 |  |  |  | 2
PB10 | Set timer device | Host, Family member | I want to schedule the device to turn on/off. | Allows the actor to turn the device on and off according to the set time. | - Click on the device you want to control. - Click on/off for lights or drag the slider from 0 to 3 for fans. |  | 1 |  |  |  | 3
PB11 | View all sensors | Host, Family member | I want to see all sensors on the current room. | Allows the actor to see all sensors of the current room they clicked. | - Click on the room you want to view. - List of all sensors of the room they clicked on. |  | 1 |  |  |  | 3
PB12 | Notify when there is an abnormality | Host | I want to receive notifications when there are abnormal changes from the sensor. | Allows Host to receive notifications about the home's status when there are abnormal changes from sensors. | - Send notification to Host when there are abnormal changes from the sensor. |  | 1 |  |  |  | 3
PB13 | Add user | Admin | I want to add user. | Allows Admin to add user. | - Log in with the admin account. - Click button [+]. - Fill information of user. - Click button [Add user]. |  | 2 |  |  |  | 3
PB14 | View all users | Admin | I want to see all users of the system. | Allows the Admin to see all Family members of the house. | - Log in with the admin account. - List of all users of the system. |  | 2 |  |  |  | 3
PB15 | Edit information of user | Admin | I want to change user information. | Allows the Admin to edit user information. | - Log in with the admin account. - List of all users of the system. - Click user want edit. - Edit information of user. - Click button [Update]. |  | 2 |  |  |  | 3
PB16 | Delete user | Admin | I want to delete user. | Allows Admin to delete Family members. | - Log in with the admin account. - List of all users of the system. - Click user want delete. - Click button [Delete]. |  | 2 |  |  |  | 3
PB03 | Log out | Admin, Host, Family member | I want to log out system so that I can stop using application | Allows the actor logout the application | - Click [⋮] icon in the upper right corner. - Click [Logout]. - Confirm account logout. |  | 3 |  |  |  | 4
PB04 | Change Password | Admin, Host, Family member | Change my password regularly | Allows the actor change password | - Click button [Change password] - Admin, Supplier, User, enter new password, confirm new password then click button [Save] |  | 3 |  |  |  | 4
PB05 | Update Information | Admin, Host, Family member | I want to update information such as full name, phone number, password. | Allows the actor update the information | - Click [⋮] icon in the upper right corner. - Click [Profile]. - Fill in the required information, press on button [Update] |  | 3 |  |  |  | 4
PB17 | Add Family member. | Host | I want to add Family member. | Allows Host to add Family members. | - Click tab [Members]. - Click button [+]. - Fill information of Family member. - Click button [Add member]. |  | 2 |  |  |  | 4
PB18 | View all Family members | Host | I want to see all Family members of the my house. | Allows the Host to see all Family members of the house. | - Click tab [Members]. - List of all Family members of the house. |  | 2 |  |  |  | 4
PB19 | Edit information of Family members | Host | I want to change Family member information. | Allows the Host to edit Family member information. | - Click tab [Members]. - List of all Family members of the house. - Click Family member want edit. - Edit information of Family member. - Click button [Update]. |  | 2 |  |  |  | 4
PB20 | Delete Family member. | Host | I want to delete Family member. | Allows Host to delete Family members. | - Click tab [Members]. - List of all Family members of the house. - Click Family member want delete. - Click button [Delete]. |  | 2 |  |  |  | 4
Note on M7: ====== ID#AAAAlzMZe58 jan samuelsson (2022-08-26 07:29:29) Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.

## Main
Scrum Project |  |  | Product Status | Done
|  |  | Sponsor | Thuan, Nguyen Tan Ph.D.
Product | DTSL
Active versions | 1
|  |  | Product Owner | Dinh, Le Nguyen Nhut
Team |  |  | Project Champion
Scrum Master | Duy, Huynh Gia |  | Other Stakeholders
Developers | Dinh, Le Nguyen Nhut
Sy, Nguyen Van
Minh, Huynh Tan Quang
Projects
Id | Description | Start | End | Status | Remarks
1 | Initial release | 2024-01-22 | 2024-02-21 | Done
| Create Proposal Document | 2024-02-02 | 2024-02-07 | Done
3 | Development | 2024-02-22 | 2024-05-16 | Done
| Sprint 1 | 2024-02-22 | 2024-03-13 | Done
| Sprint 2 | 2024-03-14 | 2024-04-03 | Done
| Sprint 3 | 2024-04-04 | 2024-04-24 | Done
| Sprint 4 | 2023-04-25 | 2024-05-15 | Done
4 | Project Meeting | 2025-05-17 | 2024-05-17 | Done
5 | Final Release | 2024-05-17 | 2024-05-17 | Done

## Sprint 1 Backlog
Sprint 1 Backlog
[10 empty] | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
1.1 |  | Sprint Planning Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.2 |  | Create Sprint Backlog for Sprint 1 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.3 |  | Update User stories | Duy | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.4 |  | Update Product backlog | Dinh | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.5 |  | Create Database Design Document | All members | Done | 12 | 12 | 0 | 12 | On Schedule | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 |  | Create Architect Design Document | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.6 |  | Create Test Plan document for Sprint 1 | Duy | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.7 |  | Create Interface Design Document | Minh | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.8 | PB1 | [ML] Train model | Duy, Minh | Done | 40 | 40 | 0 | 45 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 6 | 4 | 5 | 3 | 3 | 4 | 3 | 4 | 5 | 3 | 5 | 0 | 0 | 0 | 0 | 0
1.9 | PB2 | [FE] Convert text to sign language - Translate | Dinh | Done | 12 | 12 | 0 | 12 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.13 | PB3 | [BE] Sign up | Duy | Done | 6 | 6 | 0 | 6 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.14 | PB4 | [BE] Sign in | Duy | Done | 5 | 5 | 0 | 5 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.15 | PB5 | [BE] Log out | Dinh | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.10 | PB3 | [FE] Sign up | Dinh | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.11 | PB4 | [FE] Sign in | Dinh | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.12 | PB5 | [FE] Log out | Dinh | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1.16 |  | Design Test case for Sprint 1 | Dinh, Minh | Done | 10 | 10 | 0 | 10 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0 | 0
1.17 |  | Testing | Duy, Minh | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6 | 0 | 0 | 0 | 0
1.18 |  | Fix bug | All members | Done | 9 | 9 | 0 | 9 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0 | 0
1.19 |  | Re-testing | All members | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0
1.20 |  | Release Sprint 1 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
1.21 |  | Sprint 1 Review Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
1.22 |  | Sprint 1 Retrospective | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  |  |  | Total | 175 | 175 | 0 | 180
Burndown data
[9 empty] | Day |  | 2024-02-21 | 2024-02-22 | 2024-02-23 | 2024-02-24 | 2024-02-25 | 2024-02-26 | 2024-02-27 | 2024-02-28 | 2024-02-29 | 2024-03-01 | 2024-03-02 | 2024-03-03 | 2024-03-04 | 2024-03-05 | 2024-03-06 | 2024-03-07 | 2024-03-08 | 2024-03-09 | 2024-03-10 | 2024-03-11 | 2024-03-12 | 2024-03-13
[9 empty] | Estimate |  | 0 | 8 | 19 | 9 | 6 | 5 | 6 | 4 | 8 | 13 | 13 | 12 | 8 | 10 | 9 | 10 | 10 | 10 | 5 | 3 | 4 | 8
[9 empty] | Estimate (burndown) |  | 180 | 171.4286 | 162.8571 | 154.2857 | 145.7143 | 137.1429 | 128.5714 | 120 | 111.4286 | 102.8571 | 94.2857 | 85.7143 | 77.1429 | 68.5714 | 60 | 51.4286 | 42.8571 | 34.2857 | 25.7143 | 17.1429 | 8.5714 | -4.6185e-14
[9 empty] | Actual |  | 0 | 6 | 7 | 8 | 7 | 8 | 13 | 5 | 6 | 6 | 5 | 10 | 9 | 5 | 6 | 8 | 10 | 7 | 10 | 8 | 9 | 9
[9 empty] | Actual (burndown) |  | 180 | 174 | 167 | 159 | 152 | 144 | 131 | 126 | 120 | 114 | 109 | 99 | 90 | 85 | 79 | 71 | 61 | 54 | 44 | 36 | 27 | 18
[9 empty] | Member |  | 2024-02-22: Estimate
[9 empty] | Duy, Huynh Gia |  | 2024-02-22: 58.5
[9 empty] | Dinh, Le Nguyen Nhut |  | 2024-02-22: 56
[9 empty] | Sy, Nguyen Van |  | 2024-02-22: 13
[9 empty] | Minh, Huynh Tan Quang |  | 2024-02-22: 52.5
[9 empty] | Total |  | 2024-02-22: 180
Note on B7: ====== ID#AAAAlzMZe6E jan samuelsson (2022-10-20 13:11:21) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAlzMZe6A jan samuelsson (2022-10-20 13:11:21) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.
Note on H7: ====== ID#AAAAlzMZe6I jan samuelsson (2022-10-20 13:11:21) Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.

## Sprint 2 Backlog
Sprint 2 Backlog
[10 empty] | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
2.1 |  | Sprint Planning Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.2 |  | Create Sprint Backlog for Sprint 2 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.3 |  | Update User stories | Minh | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.4 |  | Update Product backlog | Dinh | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.5 |  | Update Database Design Document | All members | Done | 12 | 12 | 0 | 12 | On Schedule | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.6 |  | Update Architect Design Document | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.7 |  | Create Test Plan document for Sprint 2 | Duy | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.8 |  | Update Interface Design Document | Minh | Done | 12 | 12 | 0 | 12 | On Schedule | 0 | 0 | 2 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.9 |  | [BE] Convert sign language to text and voice - Translate | Duy | Done | 16 | 16 | 0 | 18 | Over Schedule | 0 | 0 | 0 | 0 | 5 | 3 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.10 |  | [BE] Create room video call | Dinh | Done | 10 | 10 | 0 | 10 | On Schedule | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.11 |  | [FE] Convert voice to sign language - Translate | Duy | Done | 12 | 12 | 0 | 13 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.12 |  | [FE] Convert sign language to text and voice - Translate | Dinh | Done | 20 | 20 | 0 | 24 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 6 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.13 |  | [FE] Create room video call | Minh | Done | 20 | 20 | 0 | 20 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 3 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2.14 |  | [FE] Convert voice to sign language - Video call | Dinh | Done | 12 | 12 | 0 | 16 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0
2.15 |  | Design test case sprint 2 | Duy, Minh | Done | 12 | 12 | 0 | 15 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 3 | 0 | 0 | 0 | 0 | 0
2.16 |  | Testing | Duy, Minh | Done | 12 | 12 | 0 | 14 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 | 0 | 0 | 0
2.17 |  | Fix bug | All members | Done | 9 | 9 | 0 | 12 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0
2.18 |  | Re-testing | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
2.19 |  | Release Sprint 2 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
2.20 |  | Sprint 2 Review Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
2.21 |  | Sprint 2 Retrospective | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  |  |  | Total | 190 | 190 | 0 | 209
Burndown data
[8 empty] | Day |  | 2024-03-14 | 2024-03-15 | 2024-03-16 | 2024-03-17 | 2024-03-18 | 2024-03-19 | 2024-03-20 | 2024-03-21 | 2024-03-22 | 2024-03-23 | 2024-03-24 | 2024-03-25 | 2024-03-26 | 2024-03-27 | 2024-03-28 | 2024-03-29 | 2024-03-30 | 2024-03-31 | 2024-04-01 | 2024-04-02 | 2024-04-03 | 2024-04-04
[8 empty] | Estimate |  | 0 | 8 | 13 | 11 | 13 | 11 | 8 | 11 | 13 | 9 | 9 | 12 | 10 | 12 | 8 | 16 | 9 | 14 | 6 | 4 | 4 | 8
[8 empty] | Estimate (burndown) |  | 209 | 199.0476 | 189.0952 | 179.1429 | 169.1905 | 159.2381 | 149.2857 | 139.3333 | 129.381 | 119.4286 | 109.4762 | 99.5238 | 89.5714 | 79.619 | 69.6667 | 59.7143 | 49.7619 | 39.8095 | 29.8571 | 19.9048 | 9.9524 | -5.6843e-14
[8 empty] | Actual |  | 0 | 10 | 7 | 8 | 7 | 18 | 5 | 9 | 8 | 13 | 6 | 5 | 6 | 10 | 9 | 8 | 10 | 7 | 7 | 16 | 10 | 12
[8 empty] | Actual (burndown) |  | 209 | 199 | 192 | 184 | 177 | 159 | 154 | 145 | 137 | 124 | 118 | 113 | 107 | 97 | 88 | 80 | 70 | 63 | 56 | 40 | 30 | 18
[10 empty] | Member | Estimate
[10 empty] | Duy, Huynh Gia | 63.5
[10 empty] | Dinh, Le Nguyen Nhut | 67
[10 empty] | Sy, Nguyen Van | 14
[10 empty] | Minh, Huynh Tan Quang | 64.5
[8 empty] | Total |  | 2024-03-15: 209

## Sprint 3 Backlog
Sprint 3 Backlog
[10 empty] | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
3.1 |  | Sprint Planning Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.2 |  | Create Sprint Backlog for Sprint 3 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.3 |  | Update User stories | Duy | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.4 |  | Update Product backlog | Dinh | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.5 |  | Update Database Design Document | All members | Done | 12 | 12 | 0 | 12 | On Schedule | 0 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.6 |  | Create Architect Design Document | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.7 |  | Create Test Plan document for Sprint 3 | Duy | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.8 |  | [BE] Convert sign language to voice - Video call | Duy | Done | 25 | 25 | 0 | 25 | On Schedule | 0 | 0 | 0 | 0 | 3 | 5 | 7 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.9 |  | [BE] Leave room | Dinh | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.10 |  | [BE] Search user | Dinh | Done | 7 | 7 | 0 | 6 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.11 |  | [BE] Add user to conversation | Minh | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.12 |  | [BE] Add message | Minh | Done | 4 | 4 | 0 | 9 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.13 |  | [FE] Convert sign language to voice - Video call | Dinh | Done | 20 | 20 | 0 | 24 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 3 | 2 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.14 |  | [FE] Send email invite user - Video call | Dinh | Done | 12 | 12 | 0 | 10 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.15 |  | [FE] Leave room | Duy | Done | 6 | 6 | 0 | 7 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.16 |  | [FE] Search user | Minh | Done | 10 | 10 | 0 | 10 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3.17 |  | [FE] Add user to conversation | Minh | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 2 | 0 | 0 | 0 | 0 | 0 | 0
3.18 |  | [FE] Add message | Minh | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
3.19 |  | Design test case sprint 3 | All members | Done | 12 | 12 | 0 | 14 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 | 0 | 0
3.20 |  | Testing | Duy, Minh | Done | 12 | 12 | 0 | 13 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 5 | 0 | 0 | 0 | 0
3.21 |  | Fix bug | All members | Done | 10 | 10 | 0 | 14 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 6 | 0 | 0 | 0
3.22 |  | Re-testing | All members | Done | 4 | 4 | 0 | 5 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0
3.23 |  | Release Sprint 3 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
3.24 |  | Sprint 3 Review Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
3.25 |  | Sprint 3 Retrospective | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  |  |  | Total | 197 | 197 | 0 | 212
Burndown data
[8 empty] | Day |  | 2024-04-03 | 2024-04-04 | 2024-04-05 | 2024-04-06 | 2024-04-07 | 2024-04-08 | 2024-04-09 | 2024-04-10 | 2024-04-11 | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24
[8 empty] | Estimate |  | 0 | 13 | 10 | 8 | 7 | 7 | 15 | 10 | 10 | 9 | 7 | 11 | 13 | 15 | 13 | 15 | 13 | 6 | 5 | 4 | 8 | 0
[8 empty] | Estimate (burndown) |  | 212 | 201.9048 | 191.8095 | 181.7143 | 171.619 | 161.5238 | 151.4286 | 141.3333 | 131.2381 | 121.1429 | 111.0476 | 100.9524 | 90.8571 | 80.7619 | 70.6667 | 60.5714 | 50.4762 | 40.381 | 30.2857 | 20.1905 | 10.0952 | -9.2371e-14
[8 empty] | Actual |  | 0 | 8 | 12 | 5 | 8 | 5 | 6 | 8 | 15 | 10 | 12 | 7 | 12 | 10 | 12 | 7 | 10 | 10 | 7 | 7 | 12 | 13
[8 empty] | Actual (burndown) |  | 212 | 204 | 192 | 187 | 179 | 174 | 168 | 160 | 145 | 135 | 123 | 116 | 104 | 94 | 82 | 75 | 65 | 55 | 48 | 41 | 29 | 16
[7 empty] | Member |  |  | 2024-04-03: Estimate
[7 empty] | Duy, Huynh Gia |  |  | 2024-04-03: 64.75
[7 empty] | Dinh, Le Nguyen Nhut |  |  | 2024-04-03: 65.25
[7 empty] | Sy, Nguyen Van |  |  | 2024-04-03: 18.25
[7 empty] | Minh, Huynh Tan Quang |  |  | 2024-04-03: 63.75
[7 empty] | Total |  |  | 2024-04-03: 212

## Sprint 4 Backlog
Sprint 4 Backlog
[10 empty] | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Story Points) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21
4.1 |  | Sprint Planning Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.2 |  | Create Sprint Backlog for Sprint 4 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.3 |  | Create Test Plan document for Sprint 4 | Duy | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.14 |  | [BE] Delete message | Minh | Done | 5 | 5 | 0 | 5 | On Schedule | 0 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.15 |  | [BE] Create user | Minh | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.16 |  | [BE] Edit user | Dinh | Done | 9 | 9 | 0 | 8 | Ahead Schedule | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.17 |  | [BE] Remove user | Dinh | Done | 7 | 7 | 0 | 7 | On Schedule | 0 | 0 | 0 | 2 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.18 |  | [BE] User detail | Dinh | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.19 |  | [BE] List conversation | Duy | Done | 6 | 6 | 0 | 6 | On Schedule | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.20 |  | [BE] List message | Duy | Done | 3 | 3 | 0 | 4 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.21 |  | [BE] List user | Minh | Done | 6 | 6 | 0 | 5 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.4 |  | [FE] Realtime mesages | Dinh | Done | 15 | 15 | 0 | 15 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 4 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.5 |  | [FE] Delete message | Minh | Done | 4 | 4 | 0 | 3 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.6 |  | [FE] Create user | Minh | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.7 |  | [FE] Edit user | Dinh | Done | 7 | 7 | 0 | 6 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.8 |  | [FE] Remove user | Dinh | Done | 3 | 3 | 0 | 3 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.9 |  | [FE] User detail | Minh | Done | 4 | 4 | 0 | 3 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.10 |  | [FE] List conversation | Duy | Done | 6 | 6 | 0 | 6 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.11 |  | [FE] List message | Minh | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.12 |  | [FE] List user | Minh | Done | 6 | 6 | 0 | 5 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.13 |  | [BE] Realtime mesages | Duy | Done | 14 | 14 | 0 | 16 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.22 |  | Final Update Proposal | Dinh | Done | 2 | 2 | 0 | 3 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.23 |  | Final Update Project Plan | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.24 |  | Final Update Product Backlog and Sprint Backlog | All members | Done | 8 | 8 | 0 | 10 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.25 |  | Final Update Architecture Document | All members | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0
4.26 |  | Final Update Database Design | All members | Done | 6 | 6 | 0 | 6 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
4.27 |  | Final Update User Interface | All members | Done | 5 | 5 | 0 | 4 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4.28 |  | Final Update Test Plan | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0
4.29 |  | Final Update Test Case | All members | Done | 8 | 8 | 0 | 10 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 6 | 0 | 0 | 0 | 0 | 0
4.30 |  | Final Update Meeting | All members | Done | 3 | 3 | 0 | 2 | Ahead Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0
4.31 |  | Design Test case for Sprint 4 | All members | Done | 10 | 10 | 0 | 10 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 0 | 0
4.32 |  | Testing | Duy, Minh | Done | 8 | 8 | 0 | 8 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0
4.33 |  | Fix bug | All members | Done | 7 | 7 | 0 | 9 | Over Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 5 | 0 | 0
4.34 |  | Re-testing | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
4.35 |  | Release Sprint 4 | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 0
4.36 |  | Sprint 4 Review Meeting | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
4.37 |  | Sprint 4 Retrospective | All members | Done | 4 | 4 | 0 | 4 | On Schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4
|  |  |  | Total | 215 | 215 | 0 | 217
Burndown data
[8 empty] | Day |  | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14 | 2024-05-15
[8 empty] | Estimate |  | 0 | 8 | 7 | 10 | 6 | 10 | 8 | 10 | 7 | 15 | 9 | 11 | 18 | 16 | 16 | 13 | 15 | 7 | 8 | 9 | 4 | 8
[8 empty] | Estimate (burndown) |  | 217 | 206.6667 | 196.3333 | 186 | 175.6667 | 165.3333 | 155 | 144.6667 | 134.3333 | 124 | 113.6667 | 103.3333 | 93 | 82.6667 | 72.3333 | 62 | 51.6667 | 41.3333 | 31 | 20.6667 | 10.3333 | -6.0396e-14
[8 empty] | Actual |  | 0 | 7 | 12 | 10 | 9 | 7 | 8 | 12 | 4 | 8 | 5 | 15 | 12 | 6 | 6 | 17 | 18 | 9 | 11 | 10 | 15 | 16
[8 empty] | Actual (burndown) |  | 217 | 210 | 198 | 188 | 179 | 172 | 164 | 152 | 148 | 140 | 135 | 120 | 108 | 102 | 96 | 79 | 61 | 52 | 41 | 31 | 16 | 0
[7 empty] | Member |  |  | 2024-04-24: Estimate
[7 empty] | Duy, Huynh Gia |  |  | 2024-04-24: 62.75
[7 empty] | Dinh, Le Nguyen Nhut |  |  | 2024-04-24: 67.75
[7 empty] | Sy, Nguyen Van |  |  | 2024-04-24: 22.75
[7 empty] | Minh, Huynh Tan Quang |  |  | 2024-04-24: 63.75
[7 empty] | Total |  |  | 2024-04-24: 217

## Retrospective
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## Impediment
Impediments
Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms